## Sheet1
QueueNumber | chng_type | Name | CommercialName | State | County | Status | TransmissionOwner | MaximumFacilityOutput | MWEnergy | MWCapacity | MWInService | CapacityorEnergy | ProjectType | Fuel | ProjectACOrDC | RightsMW | InitialStudy | FeasibilityStudy | FeasibilityStudyStatus | SystemImpactStudy | SystemImpactStudyStatus | FacilitiesStudy | FacilitiesStudyStatus | InterimInterconnectionServiceAgreement | InterimInterconnectionServiceAgreementStatus | WholesaleMarketParticipationAgreement | ConstructionServiceAgreement | ConstructionServiceAgreementStatus | UpgradeConstructionServiceAgreement | UpgradeConstructionServiceAgreementStatus | BackfeedDate | QueueDate | LongTermFirmServiceStartDate | LongTermFirmServiceEndDate | TestEnergyDate | WithdrawalDate | WithdrawnRemarks | ProjectedInServiceDate | RevisedInServiceDate | ActualInServiceDate | SuspensionDate | AttachmentType | AlternateQueue | SlideQueue
AA2-116 | + | Cook-East Elkhart 345kV | Indeck Niles Energy Center | MI | Cass | Under Construction | AEP | 994 | 994 | 994 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2116_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2116_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_116_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_116_csa.pdf | Document Posted | N/A | N/A | 6/24/2021 | 4/28/2015 | N/A | N/A | 11/21/2021 |  |  | 3/15/2022 | 3/15/2022 |  | N/A | N | No
AA2-116 | - | Cook-East Elkhart 345kV | Indeck Niles Energy Center | MI | Cass | Under Construction | AEP | 994 | 994 | 994 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2116_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2116_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_116_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_116_csa.pdf | Document Posted | N/A | N/A | 6/24/2021 | 4/28/2015 | N/A | N/A | 11/15/2021 |  |  | 3/15/2022 | 3/15/2022 |  | N/A | N | No
AB1-163 | + | Glidden-Van Hiseville 34.5 kV | Legler Landfill Solar Farm | NJ | Ocean | In Service | JCPL | 2.9 | 2.88 | 0 | 2.88 | Energy | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1163_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1163_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1163_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1163_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A | 10/30/2021 |  |  | 10/30/2021 | 10/30/2021 | 11/6/2021 | N/A | N | No
AB1-163 | - | Glidden-Van Hiseville 34.5 kV | Legler Landfill Solar Farm | NJ | Ocean | Under Construction | JCPL | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1163_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1163_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1163_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1163_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A | 10/30/2021 |  |  | 10/30/2021 | 10/30/2021 |  | N/A | N | No
AB2-190 | + | Hopewell-Surry 230kV | Fort Powhatan Solar | VA | Prince George | Partially in Service - Under Construction | Dominion | 160 | 160 | 112 | 130 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2190_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2190_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2190_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_190_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_190_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 8/6/2021 |  | Customer Milestone Not Met | 12/1/2021 | 12/1/2021 | 8/4/2021 | N/A | N | No
AB2-190 | - | Hopewell-Surry 230kV | Fort Powhatan Solar | VA | Prince George | Partially in Service - Under Construction | Dominion | 160 | 160 | 112 | 20 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2190_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2190_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2190_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_190_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_190_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 8/6/2021 |  | Customer Milestone Not Met | 12/1/2021 | 12/1/2021 | 8/4/2021 | N/A | N | No
AC1-044 | + | Kammer-Vassell 765kV | Guernsey Power Station | OH | Guernsey | Under Construction | AEP | 1650 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1044_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1044_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_044_csa.pdf | Document Posted | N/A | N/A | 9/23/2021 | 8/31/2016 | N/A | N/A | 6/11/2022 |  |  | 12/31/2022 | 12/31/2022 |  | N/A | N | No
AC1-044 | - | Kammer-Vassell 765kV | Guernsey Power Station | OH | Guernsey | Under Construction | AEP | 1650 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1044_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1044_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1044_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_044_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_044_csa.pdf | Document Posted | N/A | N/A | 9/23/2021 | 8/31/2016 | N/A | N/A | 3/24/2022 |  |  | 12/31/2022 | 12/31/2022 |  | N/A | N | No
AC1-141 | + | Cook-East Elkhart 345kV | Indeck Niles Energy Center | MI | Cass | Under Construction | AEP | 1085 | 91 | 91 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1141_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1141_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_141_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/24/2021 | 10/28/2016 | N/A | N/A | 11/21/2021 |  |  | 3/15/2022 | 3/15/2022 |  | N/A | N | No
AC1-141 | - | Cook-East Elkhart 345kV | Indeck Niles Energy Center | MI | Cass | Under Construction | AEP | 1085 | 91 | 91 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1141_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1141_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_141_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/24/2021 | 10/28/2016 | N/A | N/A | 11/15/2021 |  |  | 3/15/2022 | 3/15/2022 |  | N/A | N | No
AC1-145 | + | Gretna DP 69 kV | Whitethorn Solar | VA | Pittsylvania | In Service | Dominion | 50 | 50 | 19 | 50 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1145_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1145_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1145_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_145_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_145_csa.pdf | Document Posted | N/A | N/A | 7/1/2021 | 10/31/2016 | N/A | N/A | 9/1/2021 |  |  | 9/1/2021 | 9/1/2021 | 10/13/2021 | N/A | N | No
AC1-145 | - | Gretna DP 69 kV | Whitethorn Solar | VA | Pittsylvania | Under Construction | Dominion | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1145_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1145_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1145_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_145_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_145_csa.pdf | Document Posted | N/A | N/A | 7/1/2021 | 10/31/2016 | N/A | N/A | 9/1/2021 |  |  | 9/1/2021 | 9/1/2021 |  | N/A | N | No
AC1-174 | + | Losantville 345kV | Riverstart Solar Park | IN | Randolph | Partially in Service - Under Construction | AEP | 100 | 100 | 38 | 100 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1174_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1174_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1174_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_174_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_174_csa.pdf | Document Posted | N/A | N/A | 7/5/2021 | 10/31/2016 | N/A | N/A | 9/24/2021 |  |  | 6/1/2022 | 6/1/2022 | 9/24/2021 | N/A | N | No
AC1-174 | - | Losantville 345kV | Riverstart Solar Park | IN | Randolph | Partially in Service - Under Construction | AEP | 100 | 100 | 38 | 66 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1174_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1174_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1174_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_174_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_174_csa.pdf | Document Posted | N/A | N/A | 7/5/2021 | 10/31/2016 | N/A | N/A | 9/24/2021 |  |  | 6/1/2022 | 6/1/2022 | 9/24/2021 | N/A | N | No
AC1-175 | + | Losantville 345kV | Riverstart Solar Park | IN | Randolph | Partially in Service - Under Construction | AEP | 100 | 100 | 38 | 60 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1175_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1175_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1175_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_175_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_175_csa.pdf | Document Posted | N/A | N/A | 7/5/2021 | 10/31/2016 | N/A | N/A | 9/10/2021 |  |  | 6/1/2022 | 6/1/2022 |  | N/A | N | No
AC1-175 | - | Losantville 345kV | Riverstart Solar Park | IN | Randolph | Partially in Service - Under Construction | AEP | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1175_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1175_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1175_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_175_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_175_csa.pdf | Document Posted | N/A | N/A | 7/5/2021 | 10/31/2016 | N/A | N/A | 9/10/2021 |  |  | 6/1/2022 | 6/1/2022 |  | N/A | N | No
AC2-175 | + | Berkshire Solar 12 kV | Berkshire Solar | NJ | Morris | In Service | JCPL | 1.6 | 1.6 | 0 | 1.6 | Energy | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2175_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2175_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2175_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2175_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2017 | N/A | N/A | 9/30/2021 |  |  | 9/30/2021 | 9/30/2021 | 11/6/2021 | N/A | N | Yes
AC2-175 | - | Berkshire Solar 12 kV | Berkshire Solar | NJ | Morris | Under Construction | JCPL | 1.6 | 1.6 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2175_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2175_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2175_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2175_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2017 | N/A | N/A | 9/30/2021 |  |  | 9/30/2021 | 9/30/2021 |  | N/A | N | Yes
AD2-047 | + | Davis Creek 138 kV |  | IL | Kankakee | Active | ComEd | 200 | 200 | 34 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2047_imp.pdf | Document Posted | [7 empty] | N/A | N/A |  | 1/30/2018 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N/A | N | No
AD2-047 | - | Davis Creek 138 kV |  | IL | Kankakee | Active | ComEd | 200 | 200 | 34 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2047_fea.pdf | Document Posted |  | In Progress | [7 empty] | N/A | N/A |  | 1/30/2018 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N/A | N | No
AD2-066 | + | Mazon-Crescent Ridge 138 kV |  | IL | Grundy | Active | ComEd | 116 | 116 | 69.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2066_imp.pdf | Document Posted | [7 empty] | N/A | N/A |  | 2/28/2018 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N/A | N | No
AD2-066 | - | Mazon-Crescent Ridge 138 kV |  | IL | Grundy | Active | ComEd | 116 | 116 | 69.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2066_fea.pdf | Document Posted |  | In Progress | [7 empty] | N/A | N/A |  | 2/28/2018 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N/A | N | No
AD2-073 | + | Sanders DP 230 kV | Woodbine Road Solar | VA | Westmoreland | Partially in Service - Under Construction | Dominion | 19.9 | 19.92 | 13.32 | 19.92 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2073_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2073_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2073_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2073_wmpa.pdf | Not Required | N/A | N/A |  | 3/14/2018 | N/A | N/A |  |  |  | 12/1/2021 | 12/1/2021 | 9/2/2021 | N/A | N | No
AD2-073 | - | Sanders DP 230 kV | Woodbine Road Solar | VA | Westmoreland | Under Construction | Dominion | 19.9 | 19.92 | 13.32 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2073_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2073_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2073_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2073_wmpa.pdf | Not Required | N/A | N/A |  | 3/14/2018 | N/A | N/A |  |  |  | 12/1/2021 | 12/1/2021 |  | N/A | N | No
AD2-100 | + | Kincaid-Pana 345 kV |  | IL | Christian | Active | ComEd | 210 | 210 | 126 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2100_imp.pdf | Document Posted | [7 empty] | N/A | N/A |  | 3/21/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N/A | N | No
AD2-100 | - | Kincaid-Pana 345 kV |  | IL | Christian | Active | ComEd | 210 | 210 | 126 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2100_fea.pdf | Document Posted |  | In Progress | [7 empty] | N/A | N/A |  | 3/21/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N/A | N | No
AD2-102 | + | Wempletown 345 kV |  | IL | Winnebago | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2102_imp.pdf | Document Posted | [7 empty] | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N/A | N | No
AD2-102 | - | Wempletown 345 kV |  | IL | Winnebago | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2102_fea.pdf | Document Posted |  | In Progress | [7 empty] | N/A | N/A |  | 3/22/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N/A | N | No
AD2-159 | + | Chestnut 345kV |  | IL | Macon | Active | ComEd | 187.5 | 187.5 | 33 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2159_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2159_imp.pdf | Document Posted | [7 empty] | N/A | N/A |  | 3/26/2018 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N/A | N | No
AD2-159 | - | Chestnut 345kV |  | IL | Macon | Active | ComEd | 187.5 | 187.5 | 33 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2159_fea.pdf | Document Posted |  | In Progress | [7 empty] | N/A | N/A |  | 3/26/2018 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N/A | N | No
AE1-071 | + | Shade Gap-Roxbury 115 kV | Aspen Road Solar | PA | Franklin | Engineering and Procurement | PENELEC | 100.1 | 100.1 | 62.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1071_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1071_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_071_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_071_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2018 | N/A | N/A |  |  |  | 11/30/2023 | 11/30/2023 |  | N/A | N | No
AE1-071 | - | Shade Gap-Roxbury 115 kV |  | PA | Franklin | Active | PENELEC | 100.1 | 100.1 | 62.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1071_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1071_fac.pdf | Document Posted | [5 empty] | N/A | N/A |  | 7/31/2018 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N/A | N | No
AE2-206 | + | East Sidney-Quincy 138 kV | Clearview Solar I | OH | Champaign | Engineering and Procurement | Dayton | 99 | 99 | 41.58 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2206_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2206_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2206_fac.pdf | Document Posted | [5 empty] | N/A | N/A |  | 3/19/2019 | N/A | N/A |  |  |  | 7/1/2024 | 7/1/2024 |  | N/A | N | No
AE2-206 | - | East Sidney-Quincy 138 kV |  | OH | Champaign | Active | Dayton | 99 | 99 | 41.58 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2206_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2206_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2206_fac.pdf | Document Posted | [5 empty] | N/A | N/A |  | 3/19/2019 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N/A | N | No
AE2-218 | + | Eldean 138 kV | Eldean Solar | OH | Miami | Engineering and Procurement | Dayton | 178 | 178 | 106 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2218_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2218_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2218_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_218_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_218_csa.pdf | Document Posted | N/A | N/A |  | 3/21/2019 | N/A | N/A |  |  |  | 12/31/2024 | 12/31/2024 |  | N/A | N | No
AE2-218 | - | Eldean 138 kV |  | OH | Miami | Active | Dayton | 178 | 178 | 106 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2218_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2218_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2218_fac.pdf | Document Posted |  |  |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_218_csa.pdf | Document Posted | N/A | N/A |  | 3/21/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N/A | N | No
AE2-343 | + | Andover (Maysville) 69 kV II | Welcome Solar III, LLC | PA | Crawford | Engineering and Procurement | ATSI | 17.9 | 17.9 | 12.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2343_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2343_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2343_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_343_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_343_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2019 | N/A | N/A |  |  |  | 12/31/2023 | 12/31/2023 |  | N/A | N | No
AE2-343 | - | Andover (Maysville) 69 kV II |  | PA | Crawford | Active | ATSI | 17.9 | 17.9 | 12.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2343_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2343_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2343_fac.pdf | Document Posted | [5 empty] | N/A | N/A |  | 3/31/2019 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N/A | N | No
AF1-257 | + | Hawks 2 12 kV |  | NJ | Hunterdon | Engineering and Procurement | JCPL | 3 | 0 | 0.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1257_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1257_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_257_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/1/2023 | 9/1/2023 |  | N/A | N | No
AF1-257 | - | Hawks 2 12 kV |  | NJ | Hunterdon | Active | JCPL | 3 | 0 | 0.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1257_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1257_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_257_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 10/1/2019 |  |  | N/A | N | No
AF2-440 | + | Hillsboro-Middleboro 138 kV |  | OH | Highland | Active | AEP | 50 | 50 | 25 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2440_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2440_imp.pdf | Document Posted |  | In Progress | [5 empty] | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N/A | N | No
AF2-440 | - | Hillsboro-Middleboro 138 kV |  | N/A | N/A | Active | AEP | 50 | 50 | 25 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2440_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2440_imp.pdf | Document Posted |  | In Progress | [5 empty] | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N/A | N | No
AG1-087 | + | Milford-Cartanza 230 kV |  | DE | Sussex | Active | DPL | 440 | 440 | 119 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1087_imp.pdf | Document Posted |  | In Progress | [5 empty] | N/A | N/A |  | 7/31/2020 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N/A | N | No
AG1-087 | - | Milford-Cartanza 230 kV |  | DE | Sussex | Active | DPL | 440 | 440 | 119 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1087_imp.pdf | Document Posted | [7 empty] | N/A | N/A |  | 7/31/2020 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N/A | N | No
AG1-096 | + | Rineyville 69 kV |  | KY | Hardin | Active | EKPC | 55 | 55 | 36.6667 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1096_fea.pdf | Document Posted |  | In Progress | [7 empty] | N/A | N/A |  | 8/14/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N/A | N | No
AG1-096 | - | Rineyville 69 kV |  | KY | Hardin | Active | EKPC | 55 | 55 | 36.6667 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1096_fea.pdf | Document Posted | [9 empty] | N/A | N/A |  | 8/14/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N/A | N | No
AG1-123 | + | Amherst-Riverville138 kV |  | VA | Amherst | Active | AEP | 75 | 75 | 44.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1123_fea.pdf | Document Posted |  | In Progress | [7 empty] | N/A | N/A |  | 8/31/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N/A | N | No
AG1-123 | - | Amherst-Riverville138 kV |  | VA | Amherst | Active | AEP | 75 | 75 | 44.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1123_fea.pdf | Document Posted | [9 empty] | N/A | N/A |  | 8/31/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N/A | N | No
AG1-162 | + | Sporn 138 kV |  | WV | Mason | Active | AEP | 27.4 | 27.4 | 14.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1162_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1162_imp.pdf | Document Posted |  | In Progress | [5 empty] | N/A | N/A |  | 9/14/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N/A | N | No
AG1-162 | - | Sporn 138 kV |  | WV | Mason | Active | AEP | 33.4 | 33.4 | 17.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1162_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1162_imp.pdf | Document Posted |  | In Progress | [5 empty] | N/A | N/A |  | 9/14/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N/A | N | No
AG1-222 | + | Guardian-Twin Branch 138 kV |  | IN | Elkhart | Active | AEP | 302.2 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1222_fea.pdf | Document Posted |  | In Progress | [7 empty] | N/A | N/A |  | 9/23/2020 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N/A | N | No
AG1-222 | - | Guardian-Twin Branch 138 kV |  | IN | Elkhart | Active | AEP | 302.2 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1222_fea.pdf | Document Posted | [9 empty] | N/A | N/A |  | 9/23/2020 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N/A | N | No
AG1-351 | + | Harrison-Good Hope 138 kV |  | OH | Fairfield | Active | AEP | 142 | 58 | 34.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1351_fea.pdf | Document Posted |  | In Progress | [7 empty] | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N/A | N | No
AG1-351 | - | Harrison-Good Hope 138 kV |  | OH | Fairfield | Active | AEP | 142 | 58 | 34.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1351_fea.pdf | Document Posted | [9 empty] | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N/A | N | No
AG1-358 | + | Howard-Melmore 138 kV |  | OH | Crawford | Withdrawn | AEP | 58 | 58 | 34.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1358_fea.pdf | Document Posted | [9 empty] | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 11/8/2021 |  | 12/31/2023 |  |  | N/A | N | No
AG1-358 | - | Howard-Melmore 138 kV |  | OH | Crawford | Active | AEP | 58 | 58 | 34.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1358_fea.pdf | Document Posted | [9 empty] | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N/A | N | No
AG1-450 | + | Airey-Vienna 69 kV II |  | MD | Dorchester | Active | DPL | 125 | 25 | 25 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1450_fea.pdf | Document Posted |  | In Progress | [7 empty] | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N/A | N | No
AG1-450 | - | Airey-Vienna 69 kV II |  | MD | Dorchester | Active | DPL | 125 | 25 | 25 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1450_fea.pdf | Document Posted | [9 empty] | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N/A | N | No
AG2-012 | + | Lardin 12 kV |  | PA | Fayette | Active | APS | 0.2 | 0.165 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [8 empty] | Not Required | N/A | N/A |  | 10/14/2020 | N/A | N/A |  |  |  | 11/30/2020 |  |  | N/A | Y | No
AG2-012 | - | Lardin 12 kV |  | PA | Fayette | Active | APS | 0.2 | 0.165 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | Not Required | [8 empty] | Not Required | N/A | N/A |  | 10/14/2020 | N/A | N/A |  |  |  | 11/30/2020 |  |  | N/A | Y | No
AG2-391 | + | Route 30-Laurich 12 kV |  | OH | Montgomery | Engineering and Procurement | APS | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | Not Required |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag2391_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag2391_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 | 12/31/2023 |  | N/A | Y | No
AG2-391 | - | Route 30-Laurich 12 kV |  | OH | Montgomery | Active | APS | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | Not Required | [8 empty] | Not Required | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/21/2022 |  |  | N/A | Y | No
AG2-392 | + | Meason 12 kV |  | N/A | N/A | Engineering and Procurement | APS | 3 | 3 | 0 |  | Energy | Generation Interconnection | [5 empty] | Not Required |  |  |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag2392_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag2392_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 | 12/31/2023 |  | N/A | Y | No
AG2-392 | - | Meason 12 kV |  | N/A | N/A | Active | APS |  |  |  |  | Energy | Generation Interconnection | [5 empty] | Not Required | [8 empty] | Not Required | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/21/2022 |  |  | N/A | Y | No
AG2-586 | + | Price 69 kV |  | MD | Queen Anne's | Withdrawn | DPL | 31 | 31 | 18.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | Withdrawn | [9 empty] | N/A | N/A |  | 3/31/2021 | N/A | N/A |  | 11/11/2021 |  | 6/1/2024 |  |  | N/A | N | No
AG2-586 | - | Price 69 kV |  | MD | Queen Anne's | Active | DPL | 31 | 31 | 18.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N/A | N | No
AH1-055 | + | Kyger Creek - Don Marquis 345 kV |  | OH | Jackson | Active | OVEC | 220 | 220 | 154 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 7/13/2021 | N/A | N/A |  |  |  | 11/15/2026 |  |  | N/A | N | No
AH1-055 | - | Kyger Creek - Don Marquis 345 kV |  | OH | Jackson | Active | AEP | 220 | 220 | 154 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 7/13/2021 | N/A | N/A |  |  |  | 11/15/2026 |  |  | N/A | N | No
AH1-076 | + | Loyalhanna - Reed Junction 25 kV |  | PA | Westmoreland | Active | APS | 18 | 18 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 7/29/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N/A | N | No
AH1-076 | - | Loyalhanna Creek |  | PA | Westmoreland | Active | APS | 18 | 18 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 7/29/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N/A | N | No
AH1-105 | + | TBD 23 kV |  | DE | Kent | Withdrawn | DPL | 4 | 4 | 2.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | Withdrawn | [9 empty] | N/A | N/A |  | 8/3/2021 | N/A | N/A |  | 11/8/2021 |  | 4/1/2022 |  |  | N/A | N | No
AH1-105 | - | TBD 23 kV |  | DE | Kent | Active | DPL | 4 | 4 | 2.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 8/3/2021 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N/A | N | No
AH1-112 | + | New Meredith 23 kV |  | DE | Kent | Withdrawn | DPL | 4 | 4 | 2.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | Withdrawn | [9 empty] | N/A | N/A |  | 8/6/2021 | N/A | N/A |  | 11/8/2021 |  | 4/1/2022 |  |  | N/A | N | No
AH1-112 | - | New Meredith 23 kV |  | DE | Kent | Active | DPL | 4 | 4 | 2.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 8/6/2021 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N/A | N | No
AH1-120 | + | Felton 23kV |  | DE | Kent | Withdrawn | DPL | 4 | 4 | 2.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | Withdrawn | [9 empty] | N/A | N/A |  | 8/17/2021 | N/A | N/A |  | 11/8/2021 |  | 4/1/2022 |  |  | N/A | N | No
AH1-120 | - | Felton 23kV |  | DE | Kent | Active | DPL | 4 | 4 | 2.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 8/16/2021 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N/A | N | No
AH1-150 | + | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 1000 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 8/28/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N/A | N | No
AH1-150 | - | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N/A | N | No
AH1-151 | + | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 1200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N/A | N | No
AH1-151 | - | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N/A | N | No
AH1-155 5139596 | + | NIPS-PJM |  | N/A | N/A | Active | Northern Indiana Public Service Company |  | 3 |  |  | Energy | Long-Term Firm Transmission |  |  |  |  | https://www.pjm.com/pub/planning/project-queues/ft-feas/ah1155_fea.pdf | Executed Agreement and/or Study | [5 empty] | N/A | N/A | [5 empty] | 8/27/2021 | 12/1/2021 | 12/1/2026 | [6 empty] | N/A | PP | No
AH1-155 5139596 | - | NIPS-PJM |  | N/A | N/A | Active | Northern Indiana Public Service Company |  | 3 |  |  | Energy | Long-Term Firm Transmission | [5 empty] | In Progress | [5 empty] | N/A | N/A | [5 empty] | 8/27/2021 | 12/1/2021 | 12/1/2026 | [6 empty] | N/A | PP | No
AH1-212 | + | Bethlehem - Lilly 46 kV |  | PA | Cambria | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/7/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N/A | N | No
AH1-212 | - | Cambria Slope 34.5 kV |  | PA | Cambria | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/7/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N/A | N | No
AH1-243 | + | New Bethlehem – Armstrong 138kV |  | PA | Clarion | Active | APS | 60 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N/A | N | No
AH1-243 | - | New Bethlehem-Brookville 138kV |  | PA | Clarion | Active | APS | 60 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N/A | N | No
AH1-247 | + | Lardin - Lake Lynn 138kV |  | PA | Fayette | Active | APS | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N/A | N | No
AH1-247 | - | Lardin-LakeLynn 138kV |  | PA | Fayette | Active | APS | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N/A | N | No
AH1-248 | + | Lardin - Lake Lynn 138kV |  | PA | Fayette | Active | APS | 65 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N/A | N | No
AH1-248 | - | Lardin-Lake Lynn 138kV |  | PA | Fayette | Active | APS | 65 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N/A | N | No
AH1-257 | + | Broadway - RichLine Hill Solar 34.5 kV |  | NJ | Warren | Active | JCPL | 19.3 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N/A | N | No
AH1-257 | - | Merril Creek - Morris Park 34.5 kV |  | NJ | Warren | Active | JCPL | 19.3 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N/A | N | No
AH1-275 | + | Spence 12.47kV |  | N/A | N/A | Active | ATSI |  |  |  |  | Energy | Generation Interconnection | [5 empty] | In Progress | [9 empty] | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N/A | Y | No
AH1-276 | + | Leasure 12.47kV |  | VA | Campbell | Active | PENELEC |  |  |  |  | Energy | Generation Interconnection | [5 empty] | In Progress | [9 empty] | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N/A | Y | No
AH1-286 | + | Schoonover |  | WV | Preston | Active | PENELEC |  |  |  |  | Energy | Generation Interconnection | [5 empty] | In Progress | [9 empty] | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N/A | Y | No
AH1-290 | + | BASF - Washburn Solar 34.5 kV |  | NJ | Warren | Active | JCPL | 19.3 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 9/9/2022 |  |  | N/A | N | No
AH1-290 | - | BASF - American Can 34.5 kV |  | NJ | Warren | Active | JCPL | 19.3 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 9/9/2022 |  |  | N/A | N | No
AH1-297 | + | Kewanee - E.D. Edwards 138 kV |  | IL | Stark | Active | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N/A | N | No
AH1-297 | - | Kewanee 138 kV |  | IL | Stark | Active | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N/A | N | No
AH1-332 | + | Kittanning - Craigsville Junction 25 kV |  | PA | Armstrong | Active | APS | 19.9 | 19.9 | 11.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N/A | N | No
AH1-332 | - | Kittanning - Craigsville 25 kV |  | PA | Armstrong | Active | APS | 19.9 | 19.9 | 11.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N/A | N | No
AH1-344 | + | Sparta Solar 34.5kV |  | VA | Campbell | Active | JCPL |  |  |  |  | Energy | Generation Interconnection | [5 empty] | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/20/2023 |  |  | N/A | Y | No
AH1-370 | + | Mather - Stoney Point Junction 25 kV |  | PA | Greene | Active | APS | 8 | 8 | 5.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N/A | N | No
AH1-370 | - | Gateway Solar 34.5kV |  | PA | Greene | Active | APS | 8 | 8 | 5.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N/A | N | No
AH1-372 | + | Piney - Timblin 115 kV |  | PA | Armstrong | Active | APS | 16 | 16 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N/A | N | No
AH1-372 | - | Redbank Solar 115kV |  | PA | Armstrong | Active | APS | 16 | 16 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N/A | N | No
AH1-373 | + | Buckeye No. 3 - Cowell Junction 25kV |  | PA | Greene | Active | APS | 12.8 | 12.8 | 7.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N/A | N | No
AH1-373 | - | Buckeye No. 3-Carmichaels 12kV |  | PA | Greene | Active | APS | 12.8 | 12.8 | 7.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N/A | N | No
AH1-397 | + | Shacklesfords 34.5 kV |  | VA | King and Queen | Active | Dominion | 19.8 | 19.818 | 13.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/2/2023 |  |  | N/A | N | No
AH1-397 | - | Shacklesfords 34.5 kV |  | VA | King and Queen | Active | Dominion | 19.8 | 19.818 | 13.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/2/2023 |  |  | N/A | N | No
AH1-410 | + | Union City Tap – JK Smith 138 kV |  | KY | Madison | Active | EKPC | 68 | 68 | 40.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N/A | N | No
AH1-410 | - | Union City - JK Smith 138 kV |  | KY | Madison | Active | EKPC | 68 | 68 | 40.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N/A | N | No
AH1-466 | + | Baker - Broadford 765 kV |  | KY | Boone | Active | AEP | 600 | 600 | 360 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N/A | N | No
AH1-466 | - | Baker - Bradford 765 kV |  | KY | Boone | Active | AEP | 600 | 600 | 360 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N/A | N | No
AH1-467 | + | Baker - Broadford 765 kV |  | KY | Boone | Active | AEP | 900 | 300 | 120 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N/A | N | No
AH1-467 | - | Baker - Bradford 765 kV |  | KY | Boone | Active | AEP | 900 | 300 | 120 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N/A | N | No
AH1-476 | + | Hunterstown-Texas Eastern Tap 115 kV II |  | PA | Adams | Active | ME | 170.5 | 73 | 73 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 9/23/2024 |  |  | N/A | N | No
AH1-476 | - | Hunterstown-Texas Eastern Tap 115 kV |  | PA | Adams | Active | ME | 243.5 | 73 | 73 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/23/2024 |  |  | N/A | N | No
AH1-480 | + | Haviland – Cavett Switch 69 kV |  | OH | Van Wert | Active | AEP | 132 | 57 | 57 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N/A | N | No
AH1-480 | - | Haviland - Covett Switch 69 kV |  | OH | Van Wert | Active | AEP | 132 | 57 | 57 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N/A | N | No
AH1-501 | + | Tionesta Junction – Crown 34.5 kV |  | PA | Forest | Active | PENELEC | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N/A | N | No
AH1-501 | - | Haynie 34.5kV |  | PA | Forest | Active | PENELEC | 10 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N/A | N | No
AH1-504 | + | Lickdale 13.2kV |  | PA | Lebanon | Active | ME | 7.5 | 7.5 | 5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N/A | N | No
AH1-504 | - | Lickdale 13.8kV |  | PA | Lebanon | Active | ME | 7.5 | 7.5 | 5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N/A | N | No
AH1-510 | + | Clarence Solar 12 kV |  | IL | Will | Active | PENELEC |  |  |  |  | Energy | Generation Interconnection | [5 empty] | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N/A | Y | No
AH1-510 | - | Clarence Solar 12 kV |  | N/A | N/A | Active | PENELEC |  |  |  |  | Energy | Generation Interconnection | [5 empty] | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N/A | Y | No
AH1-511 | + | Blacklick Solar 12 kV |  | WV | Berkeley | Active | PENELEC |  |  |  |  | Energy | Generation Interconnection | [5 empty] | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N/A | Y | No
AH1-511 | - | Blacklick Solar 12 kV |  | N/A | N/A | Active | PENELEC |  |  |  |  | Energy | Generation Interconnection | [5 empty] | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N/A | Y | No
AH1-512 | + | Brush Creek Solar 12 kV |  | PA | Clearfield | Active | PENELEC |  |  |  |  | Energy | Generation Interconnection | [5 empty] | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N/A | Y | No
AH1-512 | - | Brush Creek Solar 12 kV |  | N/A | N/A | Active | PENELEC |  |  |  |  | Energy | Generation Interconnection | [5 empty] | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N/A | Y | No
AH1-513 | + | Summit Community Solar 12 kV |  | WV | Monongalia | Active | APS |  |  |  |  | Energy | Generation Interconnection | [5 empty] | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N/A | Y | No
AH1-513 | - | Summit Community Solar 12 kV |  | N/A | N/A | Active | APS |  |  |  |  | Energy | Generation Interconnection | [5 empty] | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N/A | Y | No
AH1-515 | + | Philipsburg - Shawville 13.2 kV |  | PA | Clearfield | Active | PENELEC | 5 | 5 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N/A | N | No
AH1-518 | + | Pulaski Sub-New Wilmington 69kV |  | PA | Lawrence | Active | ATSI | 19 | 19 | 7.98 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N/A | N | No
AH1-518 | - | Pulaski Sub-Volant Sub 25kV |  | PA | Lawrence | Active | ATSI | 19 | 19 | 7.98 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N/A | N | No
AH1-520 | + | Blue Jacket-Kirby 138 kV V |  | OH | Union | Active | ATSI | 120 | 120 | 79.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/15/2024 |  |  | N/A | N | No
AH1-520 | - | Blue Jacket-Kirby 138 kV III |  | OH | Union | Active | ATSI | 120 | 120 | 79.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/15/2024 |  |  | N/A | N | No
AH1-521 | + | Blue Jacket-Kirby 138 kV VI |  | OH | Union | Active | ATSI | 100 | 100 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/15/2024 |  |  | N/A | N | No
AH1-521 | - | Blue Jacket-Kirby 138 kV IV |  | OH | Union | Active | ATSI | 100 | 100 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/15/2024 |  |  | N/A | N | No
AH1-526 | + | South Canton - Sammis 345 kV |  | OH | Carroll | Active | ATSI | 80 | 80 | 33.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N/A | N | No
AH1-526 | - | South Canton - Sammis 345 kV |  | OH | Carroll | Active | AEP | 80 | 80 | 33.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N/A | N | No
AH1-537 | + | Pierce - DOE X-530 345 kV |  | OH | Highland | Active | OVEC | 178.5 | 178.5 | 107.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N/A | N | No
AH1-537 | - | Pierce - DOE X-530 345 kV |  | OH | Highland | Active | AEP | 178.5 | 178.5 | 107.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N/A | N | No
AH1-547 | + | Reynolds - Olive #1 345 kV |  | IN | White | Active | AEP | 180 | 0 | 74 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N/A | N | No
AH1-553 | + | Broadview -Tangy 138 kV II |  | OH | Madison | Active | ATSI | 66 | 66 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N/A | N | No
AH1-553 | - | East Springfield-Tangy 138 kV |  | OH | Madison | Active | ATSI | 66 | 66 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N/A | N | No
AH1-560 | + | UNIV PK E.C 138 kV |  | IL | Will | Active | ComEd | 573 | 250 | 208 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N/A | N | No
AH1-565 | + | Lemoyne 345kV |  | OH | Wood | Active | ATSI | 950 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N/A | N | No
AH1-565 | - | Lemoyne 345kV |  | OH | Wood | Active | ATSI | 1510 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N/A | N | No
AH1-591 | + | Cherry Ridge 66kV |  | WV | Grant | Active | APS | 100 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N/A | N | No
AH1-591 | - | Cherry Ridge 66kV |  | WV | Grant | Active | APS | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N/A | N | No
AH1-592 | + | Cherry Ridge 66kV |  | WV | Grant | Active | APS | 145 | 45 | 45 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N/A | N | No
AH1-592 | - | Cherry Ridge 66kV |  | WV | Grant | Active | APS | 45 | 45 | 45 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N/A | N | No
AH1-612 | + | North Orwell - East Sayre 34.5kV |  | PA | Bradford | Active | PENELEC | 7.5 | 7.5 | 5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N/A | N | No
AH1-612 | - | North Orwell 34.5kV |  | PA | Bradford | Active | PENELEC | 7.5 | 7.5 | 5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N/A | N | No
AH2-008 | + |  |  | PA | Bedford | Active | APS | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 10/6/2021 | N/A | N/A |  |  |  | 9/15/2023 |  |  | N/A | N | No
AH2-012 | + | Sinai 12.47 kV |  | VA | Halifax | Withdrawn | Dominion | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | Withdrawn | [9 empty] | N/A | N/A |  | 10/12/2021 | N/A | N/A |  | 11/12/2021 |  | 12/31/2022 |  |  | N/A | N | No
AH2-015 | + | Nelson 138 kV |  | IL | Lee | Active | ComEd | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [9 empty] | N/A | N/A |  | 10/20/2021 | N/A | N/A |  |  |  | 3/24/2025 |  |  | N/A | N | No
U4-028 | + | Fostoria Central-Greenlawn-Howard 138kV | Seneca Wind | OH | Seneca | Withdrawn | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4028_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u4028_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u4_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u4_028_csa.pdf | Document Posted | N/A | N/A |  | 12/26/2008 | N/A | N/A |  | 11/5/2021 |  | 12/31/2020 | 12/31/2020 |  | N/A | N | No
U4-028 | - | Fostoria Central-Greenlawn-Howard 138kV | Seneca Wind | OH | Seneca | Suspended | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4028_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u4028_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u4_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u4_028_csa.pdf | Document Posted | N/A | N/A |  | 12/26/2008 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 |  | N/A | N | No
U4-029 | + | Fostoria Central-Greenlawn-Howard 138kV | Seneca Wind | OH | Seneca | Withdrawn | AEP | 200 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4029_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u4029_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u4_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u4_029_csa.pdf | Document Posted | N/A | N/A |  | 12/26/2008 | N/A | N/A |  | 11/5/2021 |  | 12/31/2020 | 12/31/2020 |  | N/A | N | No
U4-029 | - | Fostoria Central-Greenlawn-Howard 138kV | Seneca Wind | OH | Seneca | Suspended | AEP | 200 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/u4029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/u4029_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/u4029_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/u4_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/u4_029_csa.pdf | Document Posted | N/A | N/A |  | 12/26/2008 | N/A | N/A |  |  |  | 12/31/2020 | 12/31/2020 |  | N/A | N | No